## Slide 1
People Strategy and Transformation: Portfolio Status Report

## Slide 2: Weekly Summary Report
Project | Project Manager | What we've DONE | What we're DOING | Where we're GOING
AES Survey | Ana Lasa / Kristi Mai/ Danielle Bootes | 9.19: Held feedback Session with Associate Listening team and Sam’s People Partners on overall FY26 AES process. 9.22: Claire reviewed AES Action Plans deck with LC. Updated AES Action Plans deck based on LC feedback for fourth People Leadership review. Completed AES Playbook and “hand-off” to People Operations team. Continued to meet with “Tiger Team” (Mackenzi) to align on next steps for Belonging and segment specific deep dives which will inform Sam’s action plans. | Iterating AES Action Plans deck with ongoing input from People Leadership team. | Associate Listening team to provide deeper dives to Sam’s People Leadership team. 9.30: Claire to share segment-specific AES action plans with Donna. 9.30: Actions plans to be completed and followed-up on a quarterly basis.
Club Enablement Role | Joann Baker | Collaborated with Ops, Safety, AP, Compliance, Credit, Membership, and GTL to build a detailed hour-by-hour 5-day training plan for Club Enablement Leads (CELs). Developed the “Day in the Life of a CEL” to outline daily responsibilities. Mapped out each CEL task as it relates to the associate experience, including: Hiring and onboarding workflows Pre-boarding coverage: orientation, expectations, and Day One readiness Me@Sams experience integration: supporting associates through tech changes, ensuring smooth adoption and usage of digital tools | Align on next steps and clarify support needs for I-9 processing. Build out the Club Enablement Lead (CEL) toolkit to support onboarding and role clarity. Share the “Day in the Life of a CEL” and the 5-day training plan with Regional Directors. Continue providing field support to ensure successful adoption and execution of the CEL role. | Finalizing and launching the Club Enablement Lead program across Clubs. Equipping leads with robust training, toolkits, and support communities. Driving measurable impact in associate engagement, tool adoption, and feedback loops. Establishing recognition and growth pathways for Club Enablement Leads. Creating a scalable model that can evolve with future initiatives and innovations.
Club Support Speed & Structure | Ana Lasa | 9.25: Held Field TA team to discuss action plan to realize future state. |  | Todd Garner to host Product and Tech mobilization meetings to align on next steps
Enhanced Hiring | Joann Baker | Initiated conversations with the GTL team to align on requirements. Received Senior Leadership approval for the proposed approach. Focus will be on: Introducing Job Previews. Enabling same-day yes/no hiring decisions. Scheduled time with the Enablement team to understand technical implications and support needs. | Finalize strategy to introduce Job Previews/Club Walks into the interview process to enhance candidate experience and decision-making. Meet with the Enablement team to begin planning integration into the Same Day Yes/No hiring process. Identified key actions needed to support Job Previews and Same Day Yes/No offers by October 20. Developed initial checklist for Club Enablement Leads to coordinate hiring and pre-boarding activities. Defined pre-boarding coverage areas: orientation, expectations, and Day One readiness. | Introduce Job Previews to improve candidate understanding and fit. Enable Same Day Yes/No hiring decisions for faster onboarding. Coordinate with the Enablement team to plan technical integration and support. Identify key actions to support Job Previews and Same Day offers. Create a checklist for Club Enablement Leads to manage hiring and pre-boarding. Define pre-boarding coverage: orientation, expectations, and Day One readiness.

## Slide 3: Weekly Summary Report
Project | Project Manager | What we've DONE | What we're DOING | Where we're GOING
Field Speed & Structure | Ana Lasa/ Kristi Mai | Met as a core team to align on continuing key workstreams despite official “on hold” status. Agreed to use the deck to track quarterly progress on Frontline Speed & Structure. Agreed on key stakeholders/counterparts moving forward: Ricardo, Joe (Srividya), Heidy (Darren), and Lacy/Kathy (H&W). | Ongoing: Track project status, maintain readiness for reactivation once prioritized. | November: Regroup ahead of leadership pulse check to ensure alignment before year-end.
Frontline Feedback | Joann Baker | Collaborating with the H&W team to understand Club org structure and training needs. Coordinating with Walmart Academy on training schedules, communications, and rollout plans. Partnering with GTL to align on feature timelines. Aligning on beta testing locations and timing; planning socialization with MPPs and People ATC Shared walking deck with Pilot People Directors and gathered feedback. Updated Feedback Training strategy: prioritize 2025 Team Leads without prior leadership training; expand to all Team Leads, then to Team Managers, Co-Managers, and Club Managers in 2026. | People Directors will meet with RGMs, MPPs, and Market Managers to socialize the pilot and drive alignment. Inform Ops ATC Will continue working with GTL to finalize travel plans for beta testing. Heidi will socialize the pilot with Darren to gain buy-in. Will meet with Club Managers to announce the new pilot and set expectations. Will work with Sam’s Comms partner to align on all communication pieces, so they can be shared with Walmart Comms partners. | October Go-Live Readiness: Finalizing all change plans and training. Seamless User Adoption: Ensuring robust training (in partnership with Walmart Academy) and support are in place to maximize user adoption and minimize disruption for the new feedback process.
New Club Support | Jennifer Dodson | Provided staffing support for the Tempe launch. Supported the member specialist transition during remodels. Introduced a new club toolkit with updated guidance and resources. Developed a comprehensive staffing strategy. Implemented tracking for training progress and headcount follow-up. Defined success measures and clarified roles for start-up environments. |  | Designing tech-enabled, people-focused clubs aligned with future job needs. Building training solutions tailored to resource-constrained start-up environments. Enhancing onboarding strategies to better support new club launches.
Career Site | Tiffany Walker | Met with GTL counterparts to gain alignment on upgrade timelines and content build roadmap Reviewed current version of Career Website; Current user facing Career site is in production with upgrades and updates being made Upgraded site currently in UAT phase | Conduct additional discussion with GTL counterparts to refine career site requirements and updates to be made Finalize timelines and content build roadmap Review job summaries and job descriptions within Workday; Identify updates to be made and develop timeline for content refinement | Continue Testing phase of Career site Refine job descriptions and job summaries

## Slide 4: Weekly Summary Report
Project | Project Manager | What we've DONE | What we're DOING | Where we're GOING
Onboarding | Joann Baker | Collaborating with the Membership team on the updated membership video: Submitted Membership Video Intake. Aligning on shoot location, script direction, creative details, and cost center. Meeting with Sam’s Compensation team to gather feedback on orientation changes: They will provide recommended verbiage for the compensation section. Continuing bi-weekly syncs with the Enterprise team to ensure orientation content is being updated. Reviewing all orientation materials, including the AEM page and Participant Deck: Additional content review is still needed. Coordinating communications next week for videos featuring Chris and Todd. Meeting with AP to share the refreshed orientation and collect feedback. | Collaborate with the Enterprise Onboarding team to finalize the refreshed orientation walking deck. Share updated orientation materials with Regional Directors for alignment. Conduct a full review of the refreshed orientation and provide feedback to the Enterprise Onboarding team. Establish a pilot timeline for select Clubs to experience the new orientation and share feedback. | Launching a refreshed onboarding experience to better support new associates and drive engagement from day one. Training our new Club Enablement Lead to facilitate the updated onboarding, ensuring consistency and energy in delivery. Establishing World-Class Onboarding: Creating a people-led, tech-powered experience that ensures associates feel valued and succeed, directly reducing turnover.
Predictive ART | Joann Baker | Finalized the Intervention Dashboard for Market People Partners (MPPs). Trained Central Region MPPs on tool functionality and use. Confirmed successful testing with Engineering—go-live approved. Launched in Central Region on Sept. 9 with minimal bugs. Sent go-live communications to stakeholders. Created Hypercare chat for Central Region support. Held first check-ins—Club Managers were engaged and pleased. | Align with People ATC and share proposal for the Oct. 7 rollout. Conduct check-ins with Central Region Clubs and monitor the Hypercare chat. Continue partnering with Product and Engineering teams to ensure readiness and support. | Expand the Predictive ART Tool to 92 clubs on 9/9/25, aiming for successful adoption. Secure resources for continued product enhancements and scalability
Tech / AI Work | Tolliver Davis | Communicated extended timeline for AI Training Pods to 11/5 Hosted 2 hour AI training with Market 9 Club and Co-Managers (~20 total field leaders of people) Secured commitment from People Product to give select group of Sam’s Home Office associates early access to all Me@Sams rollouts and enhancements | Mobilizing power team for Global People Innovation Games Continue support of pilot rollouts of new tech and me@ functionalities Finalizing detailed Squiggly release roadmap and change management plan to support chain release on 10/10 | Receive sign off from Field Leadership Team for hourly leaders of people to action TOR Share final session 4 and 5 AI Pod training curriculum content

## Slide 5: Project Portfolio Health Check
Project Status | Green | Amber | Red
AES Survey |  |  | 
Club Support - Speed & Structure |  |  | 
Club Enablement Role |  |  | 
Enhanced Hiring |  |  | 
Field - Speed & Structure |  |  | 
Frontline Feedback |  |  | 
New Club Support |  |  | 
Onboarding |  |  | 
Predictive ART |  |  | 
Tech / AI Work |  |  |